## User stories
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Owner | Muhammad Atiq 23811395
As a user, I want:
|  | No | User stories
|  | 1 | To create the snake game
|  | 2 | The game board looks like …
|  | 3 | To move snake in different directions
|  | 4 | To customize the snake colour
|  | 5 | To customize the prey colour
|  | 6 | To calculate score

## Snake-game
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Developer | Muhammad Atiq 23811395
No | Level-1 tasks | Level-2 tasks | Level-3 tasks | Priority | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Note
1 | Create a repository for the project on GitHub |  |  | 1 | 100%
2 | Create and update product backlog |  |  | 1 | 100%
2.1 | Removed all the errors and added login accounts.
3 | Build the snake game as in the product backlog |  |  | 2 | 100%
3.1 | Declared funcions in Snake, Prey, GameBoard class. | Build the GUI
3.1.1 | Applied the concept of abstractions to the snake game |  | GUI for gameboard
3.1.2 | Declared private and public funcions |  | GUI for login form
3.2 |  | Build the game logic
3.2.1 |  |  | Snake logic
4 | Test and deploy the game |  |  | 3 | 0%
5 | Document the game |  |  | 4 | 0%