## User stories
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Owner | Muhammad Atiq 23811395
As a user, I want:
|  | No | User stories
|  | 1 | To create the snake game
|  | 2 | The game board looks like …
|  | 3 | To move snake in different directions
|  | 4 | To customize the snake colour
|  | 5 | To customize the prey colour
|  | 6 | To calculate score

## Snake-game
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Developer | Muhammad Atiq 23811395
No | Level-1 tasks | Level-2 tasks | Level-3 tasks | Priority | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Note
1 | Create a repository for the project on GitHub |  |  | 1 | 100%
2 | Create and update product backlog |  |  | 1 | 100%
2.1 | Removed all the errors and added login accounts.
3 | Build the snake game as in the product backlog |  |  | 2 | 100%
3.1 | Declared funcions in Snake, Prey, GameBoard class. | Build the GUI
3.1.1 | Applied the concept of abstractions to the snake game |  | GUI for gameboard |  |  | 100%
3.1.2 | Declared private and public funcions |  | GUI for login form |  |  | 100%
3.1.3 |  |  | GUI for Snake |  |  | 100%
3.1.4 |  |  | GUI for Prey |  |  | 100%
Adding some new methods and class converted into abstract
|  |  | snake |  |  |  | 100%
|  |  | prey |  |  |  | 100%
|  |  | score Board |  |  |  | 100%
|  |  | Score Board logic |  |  |  | 100%
3.2 |  | Build the game logic
3.2.1 |  |  | Snake logic |  |  |  |  | 100%
3.2.2 |  |  | prey logic |  |  |  |  | 100%
3.2.3 |  |  | key praseed Event |  |  |  |  | 100%
3.3 | Game control
|  |  | Movement of snake is control with arrow keys | [5 empty] | 100%
|  |  | Snake stop on spacebar and resume on any arrow key | [5 empty] | 100%
|  |  | When snake hit himself or hit the border it will end the game | [5 empty] | 100%
4 | Test and deploy the game |  | All the charactors are developed | 3 |  |  |  |  | 100%
4.1 | Test the dashboard |  | Game work well except the dashboard allingment | [5 empty] | 90%
5 | Document the game |  | All the documentation and backlog is completed | 4 |  |  |  |  | 100%